## project
Project Plan
|  |  |  | Period Highlight: |  |  |  |  | 43 |  |  |  |  | Plan
| PLAN | PLAN | PLAN
ACTIVITY | PRIORITY | START | DURATION | PERIODS
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Global login | 1 | 1 | 7
View storage spaces | 1 | 8 | 3
Submit storage request (PI) | 1 | 8 | 2
Review storage requests (Approver) | 1 | 8 | 3
Approve storage requests (Approver, Admin) | 1 | 11 | 2
User access level login | 2 | 13 | 7
Granting storage access (Data Manager) | 2 | 13 | 7
Grant researchers manager-level access (PI) | 2 | 13 | 7
Additional storage request (Data Manager) | 2 | 20 | 3
Change PI of a storage space (Admin) | 2 | 23 | 4
View a list of all storage requests (Approver) | 2 | 23 | 4
Send appropriate notifications (Admin) | 3 | 27 | 3
Receiving email notifications (DM, PI, Researcher) | 3 | 27 | 3
Viewing status of requests (DM, PI) | 3 | 30 | 4
Revoking access to storage spaces (DM, PI) | 3 | 34 | 7
Add comment to a request (Admin) | 3 | 34 | 4
View a list of all storage spaces for a faculty (Approver) | 3 | 34 | 4