## Sheet1
Sprint 1
Planned Tasks | Task Distribution | Planned Effort | Actual Effort
Global login | Delan | 7 | 3
View storage spaces | Jason, Kye | 3 | 4
Submit storage request (PI) | Kye | 2 | 2
Review storage requests (Approver) | Kye | 3 | 14
Redesign of navigation bar | Luke | 0 | 1
Front-end addition of interleaved links | Luke | 0 | 1
Approve storage requests (Approver, Admin) | Jason, Kye | 2 | 14
Presentation | Jasmine, Jason | 3 | 1