## Sheet1
Sprint 3
Planned Tasks | Task Distribution | Planned Effort | Actual Effort
View a list of all storage requests | Luke, Jason, Kye | 4 | 2
Granting storage access | Luke, Jason, Kye | 7 | 4
Review storage requests | Luke, Jason, Kye | 3 | 3
Approve storage requests | Luke, Jason, Kye | 2 | 3
User access level login | Luke, Jason, Kye | 7 | 14
Grant researchers manager-level access | Luke, Jason, Kye | 2 | 4
Additional storage request | Luke, Jason, Kye | 3 | 2
Change PI of a storage space | Luke, Jason, Kye | 3 | 5
Send appropriate notifications | Luke, Jason, Kye | 3 | 3
Receiving email notifications | Luke, Jason, Kye | 4 | 3
Viewing status of requests | Luke, Jason, Kye | 7 | 2
Revoking access to storage spaces | Luke, Jason, Kye | 4 | 7
Add comment to a request | Luke, Jason, Kye | 4 | 1
View a list of all storage spaces for a faculty | Luke, Jason, Kye | 4 | 7
Meeting minutes | Rob | 1 | 2
Report | Jasmine, Callum, Luke, Jason, Rob, Delan | 14 | 14
Presentation | Jasmine, Callum, Delan | 4 | 4